## Entity Dashboard
STATUS OF PROJECTS DASHBOARD
Entity Name: ________________
Project Approved and under Execution
Sr.no | Projct ID | Name of Proposal | Category | DPR Cost | Grant Approved | Date of sanction | Grant released | % of Grant Untilised | Comletion Period | Schedule completion date | 1st Time Extention | 2nd Time Extention | 3rd Time Extention
Projects under for Examination
Sr.no | Projct ID | Name of Proposal | Category | DPR Cost | submission Date | Status of examination (Under Examination / cleared/Declined) |  |  | date of Sanction / Decline
[6 empty] | TESG | App. Co | Mo. Co
NEW Projects pending for acceptance
Sr.no | Projct ID | Name of Proposal | category | DPR Cost | submission Date | Accepted Yes/No
Projects completed
Sr.no | Projct ID | Name of Proposal | category | DPR Cost | Grant Approved | Grant released | % of Grant Untilised | Comletion Period | Schedule completion date | Actual completion date
Projects Declined
Sr.no | Projct ID | Name of Proposal | category | DPR Cost | Date of Decline
ENTITY BUDGET DASHBOARD
[5 empty] | RE FY 2020-21 |  |  |  |  | RE FY 2020-21
Sr.no | Projct ID | Name of Proposal | Grant Approved | Cumulative Grant disbusred | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
Total
ENTITY PAYMENT DASHBOARD
Sr.no | Projct ID | Name of Proposal | Grant Approved | Payment released
|  |  |  | 10% stg-1 | 20% stg-2 | 60% stg-3 | 10% stg-4 | Total
1
2
3
ENTITY OUTPUT OUTCOME DASHBOARD
Date : 08.01.2021
OUTPUTS 2021-22 | [10 empty] | OUTCOMES 2021-22
Output | Indicator (s) | Annual | Target 2021-22 |  |  |  | Progress 2021-22 |  |  |  | Outcome | Indicator (s) | Annual | Target 2021-22 |  |  |  | Progress 2021-22
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1. Enhanced execution of projects to bring improvement in grid safety and operation | 1.1.Total length of transmission line renovated and modernized (CKMs) | [9 empty] | 1. Improvement in grid safety and operation | 1.1.Increase in power transmission capacity (MVA) | bar: Progress 2021-22 Q1
| 1.1.Addition in reactive power capacity available to control voltage profile (MVAR) | [10 empty] | 1.1. Total number of substations rectified for discrepancies
1.2.Number of substations renovated and upgraded
1.3.Number of Special Energy Meters (SEM) and Phaser Measurement Units (PMUs) installed
1.4.Amount of fund utilized on approved projects (Crore)
Note on C54: Author: click the Project ID to open payment processing mdule

## Entity Payment processing modul
Payment processing Module
Entity Screen
Details of LOA placed and Eligible Grant.
Proj ID | Approved Cost | Approved Grant | LOA & Eligible Grant Details
|  |  | LOA No | LOA Value | Eligible Grant Stg-1 (10%) | Claimed Grant | Received Grant | Balance Eligible Grant | Balance Approved Grant
A | B | C | D | E | F=0.1B | K | L | M | N
1 |  |  | 1
2
3
4
5
6
7
8
9
10
Total | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Proj ID | Approved Cost | Approved Grant | STAGE-2 (20%) LOA wise grant claimed
|  |  | LOA No | LOA Value | Eligible Grant Stg-2 (20%) | Tranch-1 | Tranch-2 | Tranch-3 | Tranch-4 | Tranch-5 | Claimed Grant Total | Received Grant Total | Balance Eligible Grant | Balance Approved Grant
A | B | C | D | E | G=0.2E | [5 empty] | K | L | M | N
1 |  |  | 1
2
3
4
5
6
7
8
9
10
Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proj ID | Approved Cost | Approved Grant | STAGE-3 (60%) LOA wise grant claimed
|  |  | LOA No | LOA Value | Eligible Grant Stg-2 (20%) | Tranch-1 | Tranch-2 | Tranch-3 | Tranch-4 | Tranch-5 | Claimed Grant Total | Received Grant Total | Balance Eligible Grant | Balance Approved Grant
A | B | C | D | E | G=0.6E | [5 empty] | K | L | M | N
1 | 100 | 90 | 1 | 10 | 5.4 | [7 empty] | 5.4
|  |  | 2 | 10 | 5.4 | [7 empty] | 5.4
|  |  | 3 | 20 | 10.8 | [7 empty] | 10.8
|  |  | 4 | 30 | 16.2 | [7 empty] | 16.2
|  |  | 5 | 5 | 2.7 | [7 empty] | 2.7
|  |  | 6 | 15 | 8.1 | [7 empty] | 8.1
|  |  | 7 | 10 | 5.4 | [7 empty] | 5.4
|  |  | 8 | [9 empty] | 0
|  |  | 9 | [9 empty] | 0
|  |  | 10 | [9 empty] | 0
Total | 100 | 90 |  | 100 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0
Proj ID | Approved Cost | Approved Grant | STAGE-4 (10%) LOA wise grant claimed
|  |  | LOA No | LOA Value | Eligible Grant Stg-4 (20%) | Tranch-1 | Tranch-2 | Tranch-3 | Tranch-4 | Tranch-5 | Claimed Grant Total | Received Grant Total | Balance Eligible Grant | Balance Approved Grant
A | B | C | D | E | G=0.6E | [5 empty] | K | L | M | N
1 | 100 | 90 | 1 | 10 | 5.4
|  |  | 2 | 10 | 5.4
|  |  | 3 | 20 | 10.8
|  |  | 4 | 30 | 16.2
|  |  | 5 | 5 | 2.7
|  |  | 6 | 15 | 8.1
|  |  | 7 | 10 | 5.4
8
9
10
Total | 100 | 90 |  | 100 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Details of stagewise Payment Claimed and Received
Proj ID | Approved Cost | Approved Grant | Stagewise Claim details
|  |  | Stage | Tranch | Eligible Grant | Claimed Grant | Received Grant | Balance grant
A | B | C | D | E | F | G | H | I=F-H | J=C-F
|  |  | Stg-1 (10%) Initial | Tranch-1 | 0 | 10 | 10 | -10
|  |  | Stg-2 (20%) | Tranch-1
Tranch-2
Tranch-3
Tranch-4
Tranch-5
|  |  | Stg-3 (60%) | Tranch-1
Tranch-2
Tranch-3
Tranch-4
Tranch-5
|  |  | Stg-4 (10%) Final | Tranch-1
Tranch-2
Tranch-3
Tranch-4
Tranch-5
Note on G10: Author: click to open LOA uploading module
Note on H10: Author: Data will populate after uploading of LOA BOQ in LOA uploading Module
Note on I10: Author: Data will pupulate based on Approved grant
Note on H26: Author: Data will populate automatically after LOA module is filled up
Note on J26: Author: To be filled up by Entity

## Entity LOA upload module
| Details as per the DPR (scheme) approved for funding from PSDF | [5 empty] | letter of award placed by the entity for the items approved under the scheme
Sr. No. | Item No in the BOQ | Description of item | Qty | Unit Price With Taxes | Cost in Lakhs | Grand Total | Details of theLOA, Vender name, LOA No.and date, delivery/ completion schedule. | Package detail(As per tendering) | LOA-1 |  |  |  |  | Cost As per DPR | Qty Delivered at site (Nos)_20.06.2017 | Qty Delivered at site (Nos) | Processed bill amount |  |  | Paid bill amount |  |  | From F&A utilization | Remarks |  | Balance Quantity | LOA-2 |  |  |  | Cost As per DPR | Qty Delivered at site (Nos)_20.06.2017 | Qty Delivered at site (Nos) | Processed bill amount |  |  | Paid bill amount |  |  | From F&A utilization | Remarks |  | Balance Quantity
[9 empty] | Qty (Nos) | Unit price Rs with taxes |  | Awarded cost Rs. with taxes |  |  |  |  | with taxes | State level taxes | without State Level taxes | Less VAT | Less Retention Money | Net paid | Net paid |  |  |  | Qty (Nos) | Unit price Rs with taxes | Awarded cost Rs. with taxes |  |  |  |  | with taxes | State level taxes | without State Level taxes | Less VAT | Less Retention Money | Net paid | Net paid
1 | 1.01 | 220kV CB (1-pole) | 18 | 1912226.5683 | 34420078.2293 | 70587558.2051 | Hi Tech Corporation, AEGCL/MD/Tech-589/PSDF/CB/220kV/25 dated07.03.2016 | Package A (220kV CB 1-Pole/3-Pole) | 19 | 1898588.5526 | 1812795.5263 | 36073183 | 34443115 | 70587558.2051 | 19 | 10 | 18281490 | 827690 | 17453800 | 993228 | 914074.5 | 16374187.5 | 16374186 |  | #REF! | -1 |  |  |  | 0 | 0 | 19 | 10 | 18281490 | 827690 | 17453800 | 993228 | 914074.5 | 16374187.5 | 16374186 |  | #REF! | 0
| 1.02 | 220kV CB (3-pole) | 18 | 2009304.4431 | 36167479.9758 |  | Hi Tech Corporation, AEGCL/MD/Tech-589/PSDF/CB/220kV/26 dated07.03.2016 | Package B (220kV CB 1-Pole/3-Pole) | 17 | 1932316.4706 | 1845764.7059 | 32849380 | 31378000 |  | 17 | 7 | 12991950 | 582950 | 12409000 | 699540 | 649597.5 | 11642812.5 | 11642811 | Mandatory Spare Items: Closing Coil, Tripping Coil, Spring Charging Motor, SF6 Gas density Motor, Set of all Gasket used sealing agent has not been supplied and shall be supplied along with the second lot. Only CB operating mechanism has been supplied |  | 1 |  |  |  | 0 |  | 17 | 7 | 12991950 | 582950 | 12409000 | 699540 | 649597.5 | 11642812.5 | 11642811 | Mandatory Spare Items: Closing Coil, Tripping Coil, Spring Charging Motor, SF6 Gas density Motor, Set of all Gasket used sealing agent has not been supplied and shall be supplied along with the second lot. Only CB operating mechanism has been supplied |  | 0
132 kV CB | [6 empty] | 132 KV CB | [18 empty] | 0 | [16 empty] | 0
2 | 1.03 | 132 kV (3-Pole) | 119 | 1058678.1796 | 125982703.3692 | 125982703.3692 | Hi Tech Corporation, AEGCL/MD/Tech-590/PSDF/CB/132kV/29 dated07.03.2016 | Package A (132 kV CB) | 41 | 799390.2439 | 763424.1463 | 32775000 | 31300390 | 125982703.3692 | 41 | 41 | 31314710 | 1413510 | 29901200 | 1696212 | 1565735.5 | 28052763 | 28052757 |  |  | 78 |  |  |  | 0 | 0 | 41 | 41 | 31314710 | 1413510 | 29901200 | 1696212 | 1565735.5 | 28052763 | 28052757 |  |  | 0
[7 empty] | Hi Tech Corporation, AEGCL/MD/Tech-590/PSDF/CB/132kV/30 dated07.03.2016 | Package B (132 kV CB) | 41 | 808201.7073 | 771754.6341 | 33136270 | 31641940 |  | 41 | 41 | 31592330 | 1462030 | 30130300 | 1715676 | 1579616.5 | 28297037.5 | 28297032 |  |  | -41 |  |  |  | 0 |  | 41 | 41 | 31592330 | 1462030 | 30130300 | 1715676 | 1579616.5 | 28297037.5 | 28297032 |  |  | 0
[7 empty] | Hi Tech Corporation, AEGCL/MD/Tech-590/PSDF/CB/132kV/31 dated07.03.2016 | Package C (132 kV CB) | 37 | 801807.8378 | 765913.5135 | 29666890 | 28338800 |  | 37 | 37 | 27511590 | 1235790 | 26275800 | 1482948 | 1375579.5 | 24653062.5 | 24653058 |  |  | -37 |  |  |  | 0 |  | 37 | 37 | 27511590 | 1235790 | 26275800 | 1482948 | 1375579.5 | 24653062.5 | 24653058 |  |  | 0
66kV & 33kV CB | [6 empty] | 66kV, 33kV CB | [18 empty] | 0 | [16 empty] | 0
3 | 1.04 | 66 kV CB | 21 | 750410.321 | 15758616.7408 | 111988240.0177 | Hi Tech Corporation, AEGCL/MD/Tech-591/PSDF/CB/66 & 33 kV/20 dated07.03.2016 | Package D (66 kV CB) | 19 | 691484.8158 | 660148.2368 | 13138211.5 | 12542816.5 | 111988240.0177 | 19 | 19 | 12603210 | 573010 | 12030200 | 687612 | 630160.5 | 11285437.5 | 11285437 |  |  | 2 |  |  |  | 0 | 0 | 19 | 19 | 12603210 | 573010 | 12030200 | 687612 | 630160.5 | 11285437.5 | 11285437 |  |  | 0
| 1.05 | 33 kV CB | 143 | 672934.4285 | 96229623.2769 |  | Hi Tech Corporation, AEGCL/MD/Tech-591/PSDF/CB/66 & 33 kV/17 dated07.03.2016 | Package A (33 kV CB) | 52 | 439502.5962 | 419517.4038 | 22854135 | 21814905 |  | 52 | 30 | 12413220 | 566820 | 11846400 | 680184 | 620661 | 11112375 | 11112375 |  |  | 91 |  |  |  | 0 |  | 52 | 30 | 12413220 | 566820 | 11846400 | 680184 | 620661 | 11112375 | 11112375 |  |  | 0
[7 empty] | Hi Tech Corporation, AEGCL/MD/Tech-591/PSDF/CB/66 & 33 kV/18 dated07.03.2016 | Package B (33 kV CB) | 47 | 438019.3617 | 418152.1277 | 20586910 | 19653150 |  | 47 | 27 | 11153160 | 507960 | 10645200 | 609552 | 557658 | 9985950 | 9985950 |  |  | -47 |  |  |  | 0 |  | 47 | 27 | 11153160 | 507960 | 10645200 | 609552 | 557658 | 9985950 | 9985950 |  |  | 0
[7 empty] | Hi Tech Corporation, AEGCL/MD/Tech-591/PSDF/CB/66 & 33 kV/19 dated07.03.2016 | Package C (33 kV CB) | 44 | 442187.8409 | 422173.9773 | 19456265 | 18575655 |  | 44 | 44 | 18405860 | 836660 | 17569200 | 1003992 | 920293 | 16481575 | 16481575 |  |  | -44 |  |  |  | 0 |  | 44 | 44 | 18405860 | 836660 | 17569200 | 1003992 | 920293 | 16481575 | 16481575 |  |  | 0
Total | [6 empty] | Total |  |  |  |  | 240536244.5 | 10 |  |  |  | 176267520 |  | 168261100 | 9568944 |  | 157885200.5 | 157885181 | [6 empty] | 10 |  |  |  | 176267520 |  | 168261100 | 9568944 |  | 157885200.5 | 157885181
[16 empty] | 115 | [16 empty] | 115
[16 empty] | 98 | [16 empty] | 98
Note on B2: Author: already filled up by Admin as per approved BOA
Note on K3: Author: To be filled by Entity as per LOA BOQ
Note on AJ3: Author: To be filled by Entity as per LOA BOQ
Note on N17: Author: This value will automatically populated in Payment Processing module
Note on AM17: Author: This value will automatically populated in Payment Processing module